## projects
ProjectID | ProjectName | Sector | Region | VRP | VisionPillar | AgencyID | Priority | Status | BaselineStartDate | BaselineEndDate | ForecastEndDate | ActualEndDate | AllocatedBudget_SAR | SpentBudget_SAR | ProgressPct | RiskLikelihood | RiskImpact | FTE_Total | OutcomeTarget_2025 | OutcomeActual_YTD | LocalContentPct | PPP_or_PIF | HasPermittingIssues
P001 | Smart Port Upgrade | Transport | Eastern | Logistics | Thriving Economy | A01 | A | On Track | 2024-01-01 | 2025-12-31 | 2025-12-31 |  | 800000000 | 320000000 | 0.45 | Medium | Medium | 120 | 100 | 40 | 0.35 | PPP | No
P002 | Regional Hospital Expansion | Health | Riyadh | Health Sector | Vibrant Society | A02 | A | At Risk | 2023-06-01 | 2025-06-30 | 2025-10-31 |  | 1200000000 | 700000000 | 0.6 | High | High | 250 | 200 | 110 | 0.25 | GovBudget | Yes
P003 | Heritage Site Restoration | Culture | AlUla | Tourism | Vibrant Society | A03 | B | Delayed | 2023-03-01 | 2024-12-31 | 2025-05-31 |  | 200000000 | 150000000 | 0.55 | Medium | High | 80 | 50 | 28 | 0.4 | PIF | No
P004 | Smart City Fiber Backbone | ICT | Makkah | Digital Government | Thriving Economy | A04 | A | On Track | 2024-02-15 | 2026-03-31 | 2026-03-31 |  | 950000000 | 210000000 | 0.3 | Low | Medium | 140 | 150 | 35 | 0.32 | PPP | No
P005 | Renewable Solar Farm 300MW | Energy | Tabuk | Energy | Thriving Economy | A05 | A | On Track | 2023-11-01 | 2025-09-30 | 2025-08-31 |  | 2200000000 | 980000000 | 0.65 | Medium | Medium | 180 | 300 | 180 | 0.5 | PIF | No
P006 | Red Sea Tourism Hub Phase 1 | Culture | Tabuk | Tourism | Vibrant Society | A03 | A | On Track | 2024-04-01 | 2026-12-31 | 2026-12-31 |  | 1500000000 | 420000000 | 0.42 | Medium | Medium | 160 | 120 | 55 | 0.38 | PPP | No
P007 | NEOM Logistics Corridor | Transport | Tabuk | Logistics | Thriving Economy | A01 | A | At Risk | 2023-10-15 | 2026-06-30 | 2026-09-30 |  | 1800000000 | 760000000 | 0.58 | High | High | 220 | 180 | 95 | 0.3 | PIF | Yes
P008 | Riyadh Metro Line Extension | Transport | Riyadh | Urban Mobility | Thriving Economy | A01 | A | On Track | 2024-01-20 | 2027-03-31 | 2027-03-31 |  | 3200000000 | 950000000 | 0.33 | Medium | High | 350 | 300 | 120 | 0.45 | GovBudget | No
P009 | National Data Center Cluster | ICT | Eastern | Digital Government | Thriving Economy | A04 | A | On Track | 2024-05-10 | 2026-09-30 | 2026-09-30 |  | 1100000000 | 240000000 | 0.27 | Low | Medium | 140 | 130 | 40 | 0.28 | PPP | No
P010 | Water Desalination Plant Upgrade | Utilities | Eastern | Water Security | Thriving Economy | A05 | A | Delayed | 2023-07-01 | 2025-12-31 | 2026-04-30 |  | 900000000 | 610000000 | 0.66 | Medium | High | 190 | 220 | 160 | 0.35 | PIF | Yes
P011 | Medina Healthcare Campus | Health | Medina | Health Sector | Vibrant Society | A02 | B | On Track | 2024-02-01 | 2026-10-31 | 2026-10-31 |  | 1350000000 | 430000000 | 0.34 | Medium | Medium | 210 | 180 | 70 | 0.32 | GovBudget | No
P012 | Green Hydrogen Pilot | Energy | NEOM | Energy | Thriving Economy | A05 | A | On Track | 2024-03-01 | 2025-11-30 | 2025-11-30 |  | 500000000 | 190000000 | 0.52 | Low | Medium | 85 | 60 | 35 | 0.62 | PIF | No
P013 | Taif Ring Road Expansion | Transport | Mecca | Logistics | Thriving Economy | A01 | B | At Risk | 2023-12-15 | 2026-01-31 | 2026-05-31 |  | 800000000 | 370000000 | 0.49 | High | Medium | 130 | 110 | 60 | 0.36 | GovBudget | Yes
P014 | Digital ID & e-Services 2.0 | ICT | Riyadh | Digital Government | Thriving Economy | A04 | A | On Track | 2024-04-15 | 2026-02-28 | 2026-02-28 |  | 420000000 | 120000000 | 0.29 | Low | Low | 95 | 100 | 32 | 0.55 | PPP | No
P015 | AlUla Heritage Trails | Culture | AlUla | Tourism | Vibrant Society | A03 | B | On Track | 2024-01-05 | 2025-10-31 | 2025-10-31 |  | 180000000 | 72000000 | 0.4 | Low | Medium | 60 | 45 | 22 | 0.48 | GovBudget | No

## milestones
ProjectID | MilestoneID | MilestoneName | PlannedDate | ForecastDate | ActualDate | MilestoneStatus | CriticalPath
P001 | M1 | Design Complete | 2024-06-30 | 2024-06-30 | 2024-06-28 | Completed | Yes
P001 | M2 | Procurement Award | 2024-10-31 | 2024-11-15 |  | In Progress | Yes
P002 | M1 | Groundbreaking | 2023-09-01 | 2023-09-10 | 2023-09-12 | Completed | Yes
P002 | M2 | Structural Completion | 2024-12-15 | 2025-02-20 |  | Delayed | Yes
P003 | M1 | Archaeology Permits | 2023-05-31 | 2023-08-15 | 2023-08-10 | Completed | Yes
P004 | M1 | Backbone Design | 2024-07-15 | 2024-07-28 | 2024-07-26 | Completed | Yes
P005 | M1 | Site Preparation | 2024-03-31 | 2024-04-10 | 2024-04-08 | Completed | Yes
P005 | M2 | Panel Installation Start | 2024-09-30 | 2024-10-05 |  | In Progress | Yes
P006 | M1 | Concept Approval | 2024-05-31 | 2024-06-10 | 2024-06-09 | Completed | Yes
P006 | M2 | Design Complete | 2025-01-31 | 2025-02-12 |  | In Progress | Yes
P007 | M1 | Land Acquisition | 2024-02-28 | 2024-03-15 | 2024-03-18 | Completed | Yes
P007 | M2 | Contract Award | 2024-09-30 | 2024-10-20 |  | Delayed | Yes
P008 | M1 | Feasibility Study | 2024-03-31 | 2024-04-05 | 2024-04-03 | Completed | Yes
P008 | M2 | Tunnel Boring Start | 2025-02-28 | 2025-03-12 |  | In Progress | Yes
P009 | M1 | Data Hall Design | 2024-07-31 | 2024-08-05 | 2024-08-04 | Completed | Yes
P010 | M1 | EPC Award | 2024-01-31 | 2024-02-20 | 2024-02-18 | Completed | Yes
P010 | M2 | Commissioning Start | 2025-10-31 | 2026-02-15 |  | Delayed | Yes
P011 | M1 | Groundbreaking | 2024-04-01 | 2024-04-10 | 2024-04-08 | Completed | Yes
P012 | M1 | Electrolyzer Delivery | 2024-09-30 | 2024-10-08 |  | In Progress | Yes
P013 | M1 | Utilities Relocation | 2024-05-31 | 2024-06-20 | 2024-06-22 | Completed | Yes
P014 | M1 | Alpha Release | 2024-12-15 | 2025-01-10 |  | In Progress | Yes
P015 | M1 | Trail Mapping | 2024-04-30 | 2024-05-08 | 2024-05-06 | Completed | Yes

## finance monthly
ProjectID | YearMonth | PlannedSpend_SAR | ActualSpend_SAR | Commitments_SAR | EV_SAR | PV_SAR | AC_SAR | EAC_SAR
P001 | 2024-01 | 20000000 | 18000000 | 15000000 | 16000000 | 20000000 | 18000000 | 820000000
P001 | 2024-02 | 22000000 | 21000000 | 10000000 | 20000000 | 22000000 | 21000000 | 815000000
P002 | 2024-01 | 50000000 | 60000000 | 45000000 | 52000000 | 50000000 | 60000000 | 1220000000
P002 | 2024-02 | 52000000 | 54000000 | 30000000 | 53000000 | 52000000 | 54000000 | 1215000000
P003 | 2024-01 | 8000000 | 7000000 | 6000000 | 6500000 | 8000000 | 7000000 | 205000000
P004 | 2024-03 | 15000000 | 12000000 | 10000000 | 11000000 | 15000000 | 12000000 | 960000000
P005 | 2024-01 | 90000000 | 95000000 | 70000000 | 88000000 | 90000000 | 95000000 | 2190000000
P005 | 2024-02 | 95000000 | 97000000 | 65000000 | 92000000 | 95000000 | 97000000 | 2185000000
P006 | 2024-05 | 30000000 | 28000000 | 25000000 | 26000000 | 30000000 | 28000000 | 1490000000
P006 | 2024-06 | 35000000 | 34000000 | 27000000 | 30000000 | 35000000 | 34000000 | 1485000000
P006 | 2024-07 | 38000000 | 36000000 | 29000000 | 32000000 | 38000000 | 36000000 | 1480000000
P007 | 2024-01 | 45000000 | 42000000 | 32000000 | 38000000 | 45000000 | 42000000 | 1790000000
P007 | 2024-02 | 46000000 | 47000000 | 35000000 | 42000000 | 46000000 | 47000000 | 1785000000
P007 | 2024-03 | 50000000 | 52000000 | 37000000 | 45000000 | 50000000 | 52000000 | 1780000000
P008 | 2024-02 | 55000000 | 52000000 | 40000000 | 43000000 | 55000000 | 52000000 | 3180000000
P008 | 2024-03 | 60000000 | 58000000 | 42000000 | 46000000 | 60000000 | 58000000 | 3175000000
P009 | 2024-06 | 22000000 | 20000000 | 16000000 | 17000000 | 22000000 | 20000000 | 1095000000
P009 | 2024-07 | 26000000 | 23000000 | 18000000 | 19000000 | 26000000 | 23000000 | 1092000000
P010 | 2024-01 | 38000000 | 40000000 | 30000000 | 34000000 | 38000000 | 40000000 | 895000000
P010 | 2024-02 | 36000000 | 37000000 | 28000000 | 32000000 | 36000000 | 37000000 | 892000000
P011 | 2024-03 | 30000000 | 28000000 | 21000000 | 22000000 | 30000000 | 28000000 | 1340000000
P011 | 2024-04 | 32000000 | 31000000 | 23000000 | 24000000 | 32000000 | 31000000 | 1335000000
P012 | 2024-03 | 18000000 | 17000000 | 14000000 | 15000000 | 18000000 | 17000000 | 495000000
P012 | 2024-04 | 20000000 | 21000000 | 15000000 | 17000000 | 20000000 | 21000000 | 492000000
P013 | 2024-02 | 24000000 | 22000000 | 17000000 | 18000000 | 24000000 | 22000000 | 795000000
P013 | 2024-03 | 26000000 | 25000000 | 18000000 | 19000000 | 26000000 | 25000000 | 792000000
P014 | 2024-05 | 12000000 | 11000000 | 9000000 | 9500000 | 12000000 | 11000000 | 418000000
P014 | 2024-06 | 14000000 | 13000000 | 10000000 | 10500000 | 14000000 | 13000000 | 416000000
P015 | 2024-02 | 6000000 | 5500000 | 4000000 | 4500000 | 6000000 | 5500000 | 178000000
P015 | 2024-03 | 7000000 | 6800000 | 4500000 | 5200000 | 7000000 | 6800000 | 176500000

## issuesrisks
ProjectID | RecordID | Type | Category | Severity | OpenDate | CloseDate | Status | Owner
P002 | IR-1001 | Issue | Permitting | High | 2024-03-10 |  | Open | Regulatory Affairs
P002 | IR-1002 | Risk | Vendor | Medium | 2024-05-01 |  | Mitigating | Procurement
P003 | IR-2001 | Issue | Procurement | Medium | 2024-02-15 | 2024-04-20 | Closed | Procurement
P004 | IR-3001 | Risk | Scope | Low | 2024-06-01 |  | Mitigating | PMO
P005 | IR-4001 | Issue | Finance | Medium | 2024-07-05 |  | Open | Treasury
P006 | IR-5001 | Risk | Environmental | Medium | 2024-07-10 |  | Mitigating | ESG Team
P006 | IR-5002 | Issue | Design | Low | 2024-08-05 | 2024-08-22 | Closed | Engineering
P007 | IR-6001 | Issue | Right of Way | High | 2024-02-12 |  | Open | Legal Affairs
P007 | IR-6002 | Risk | Vendor | Medium | 2024-04-01 |  | Mitigating | Procurement
P008 | IR-7001 | Issue | Permitting | Medium | 2024-03-18 | 2024-05-09 | Closed | Regulatory Affairs
P008 | IR-7002 | Risk | Supply Chain | High | 2024-06-25 |  | Mitigating | PMO
P009 | IR-8001 | Issue | Cooling Systems | Medium | 2024-08-01 |  | Open | Operations
P010 | IR-9001 | Risk | Schedule | High | 2024-05-20 |  | Mitigating | PMO
P011 | IR-9101 | Issue | Contract | Medium | 2024-06-15 | 2024-07-10 | Closed | Contracts
P012 | IR-9201 | Risk | Safety | Low | 2024-05-30 |  | Mitigating | HSE
P013 | IR-9301 | Issue | Utilities | Medium | 2024-03-09 |  | Open | Engineering
P014 | IR-9401 | Risk | Scope | Low | 2024-07-22 |  | Mitigating | Product Owner
P015 | IR-9501 | Issue | Community | Low | 2024-04-18 | 2024-05-02 | Closed | CSR

## agencies
AgencyID | AgencyName | CSAT | CES | AvgResponseDays | DigitalMaturityScore
A01 | Ministry of Transport | 82 | 78 | 6 | 3.5
A02 | Ministry of Health | 76 | 72 | 9 | 3
A03 | Ministry of Culture | 88 | 80 | 5 | 3.8
A04 | Digital Government Authority | 84 | 79 | 7 | 3.9
A05 | Ministry of Energy | 81 | 77 | 8 | 3.6
A06 | Ministry of Municipal & Rural Affairs | 79 | 74 | 10 | 3.4
A07 | NEOM Authority | 85 | 81 | 6 | 4.1
A08 | Red Sea Global | 88 | 83 | 5 | 4